## Daily Plan
eie-Dubai Global Scholars' Hunt: daily ad budget plan (Rs)
Prepared by HSIM (Hindustan School of Internet Marketing) for Turning Point Studies Consultants Pvt. Ltd. Planning figures, not guarantees.
Date | Day | Phase | Meta | Google Search | YouTube | Retargeting | Day total | Cumulative | Note
2026-10-25 | Sun | Test | 2200 | 1000 | 300 | 0 |  |  | Ads go live; test 4 creatives x 3 audiences
2026-10-26 | Mon | Test | 2200 | 1000 | 300 | 0
2026-10-27 | Tue | Test | 2100 | 1000 | 400 | 0
2026-10-28 | Wed | Learn | 3200 | 1300 | 700 | 800 |  |  | Scale winners; retargeting starts
2026-10-29 | Thu | Learn | 3200 | 1300 | 700 | 800
2026-10-30 | Fri | Learn | 3200 | 1300 | 700 | 800 |  |  | Creator wave 1 starts (3 nano)
2026-10-31 | Sat | Learn | 3200 | 1300 | 700 | 800
2026-11-01 | Sun | Learn | 3200 | 1300 | 700 | 800
2026-11-02 | Mon | Learn | 3000 | 1500 | 500 | 1000
2026-11-03 | Tue | Build-up | 4500 | 1800 | 1000 | 1700 |  |  | Diwali creatives; YouTube Shorts push
2026-11-04 | Wed | Build-up | 4500 | 1800 | 1000 | 1700
2026-11-05 | Thu | Build-up | 4500 | 1900 | 1000 | 1600 |  |  | Creator wave 2 starts (2 micro + 3 nano)
2026-11-06 | Fri | Diwali peak | 9100 | 2900 | 1200 | 800 |  |  | Dhanteras
2026-11-07 | Sat | Diwali peak | 10400 | 3300 | 1400 | 900 |  |  | Choti Diwali
2026-11-08 | Sun | Diwali peak | 11700 | 3800 | 1500 | 1000 |  |  | Diwali: heaviest day
2026-11-09 | Mon | Diwali peak | 10800 | 3500 | 1400 | 800 |  |  | Govardhan Puja
2026-11-10 | Tue | Last call | 7000 | 2500 | 800 | 800 |  |  | Last call: urgency + countdown
2026-11-11 | Wed | Last call | 7000 | 2500 | 700 | 700 |  |  | Registrations close tonight
Total ads
Rules
Raise an ad set's budget by at most 20% a day, and only while cost per registration stays under Rs 600.
Pause any ad set that spends Rs 1,500 without a single paid registration.
Check results every evening; if Diwali peak days run above Rs 667 per registration, hold spend and call Turning Point.

## Budget Summary
Total budget split (Rs 2,00,000)
Line | Budget | Share | Plan check
Meta (Facebook + Instagram)
Google Search
YouTube Shorts + Demand Gen
Retargeting (Meta + YouTube)
Influencers | 40000
Total
What the budget buys (300 paid registrations at Rs 999 = Rs 2,99,700)
Scenario | Cost per registration | Spend for 300 | Left of Rs 2,00,000
Optimistic | 350
Base | 450
Conservative | 600
Break-even ceiling | 667

## Influencers
Influencer plan (Rs 40,000)
Item | Count | Fee each | Total
Micro creators (50k to 2L followers) | 2 | 6000
Nano creators (10k to 50k followers) | 6 | 2000
Results pool (Rs 150 per verified paid registration via code, capped; about 93 registrations) | 1 | 14000
Tracking links, codes, contingency | 1 | 2000
Total
Schedule
Wave 1: 3 nano creators post 30 Oct to 1 Nov.
Wave 2: 2 micro + 3 nano creators post 5 to 8 Nov (Diwali peak).
Fixed fee: 50% advance, 50% after the post is live with screenshot and insights.
Results pool paid after 15 Nov; unspent amount stays with Turning Point.